Friends for life:
Running an

assisted holiday project

A Manual of Best Practice

EMIGRANT ADVICE NETWORK

www.ean.ie

Version: June 2008

Emigrant Advice Network (EAN)

Who are we?

EAN is an independent emigration network, comprised of statutory and voluntary agencies, as well as individuals and academics interested in emigration from Ireland and return migration to Ireland. Our aim is to improve the quality of the emigrant experience. The only qualification for membership is to have an interest in migration and migrant issues.

EAN is similar in structure to the Federation of Irish Societies (FIS) in the UK and the Coalition of Irish Immigration Centers in the US. The organisation was launched in 1996 by then-President Mary Robinson. The launch followed a recommendation from a FÁS-financed conference on migration that collaboration and networking between agencies in Ireland and abroad needed improvement and consistency.

EAN’s objectives include:

- To develop the network as a locus of unity and communication between members in Ireland

- To offer a common voice in advocacy work

- To develop capacities for using the media in service of our mission

- To retain our emphasis on personal connectedness

- To proactively support the work of those ‘in the field’

- To undertake projects of benefit to emigrants

- To maintain connections with umbrella bodies, assist newly developing entities, and reach out to parts of the world where there are no umbrella bodies.

Index

Background Information

The Task Force Report

Terms of Reference

What is an assisted holiday?

Who can benefit?

What can participants gain?

Why is there a need?

How can the holiday be funded?

How to divide costs

How to generate income

Keep costs to a minimum

Where to stay?

How to travel?

How long?

How many participants?

What kind of support?

Where?

What will participants do?

What information collect?

Take the first steps

What are the duties of the sending group?

What will the host group do?

Activities to consider

Ensure health and safety

Involve the participants

Appendices

Personal Information Sheet

Consent Form

Risk Assessment Form

Critical Path Analysis

The Monaghan Experience

The Clare Experience

Useful Address Section

Background to the Assisted Holidays project

The Task Force – Ireland and The Irish Abroad, August 2002

The Task Force on Policy Regarding Emigrants was established in 2001 by the Minister for Foreign Affairs to “address the special needs of those Irish emigrants abroad who are particularly marginalised or at greatest risk of exclusion”

The Task Force, which included representatives from Ireland, Britain and the United States, travelled to emigrant communities around the world, consulting with individuals and groups on a broad range of matters affecting emigrants. The report, published in 2002, made a series of recommendations on improving emigrant welfare.

One of the priority recommendations was the development of assisted holidays for older emigrants. The report said:

“The Task Force recommends that a ‘Holiday in Ireland’ scheme be introduced to enable Irish elderly abroad, especially people in Britain who are unable to return permanently to retain links with their relatives and friends in Ireland. It recommended a pilot scheme be set up in Britain and for it to be reviewed after three years with a view to the possibility of extending it to other countries.”

(Report of the Task Force on Policy Regarding Emigrants, Section 6.18)

“The Task force also recommends there should be an allocation of funding to assist the “Holiday in Ireland Project” for those who are not in a position to return home permanently.”

(Report of the Task Force on Policy Regarding Emigrants, Section 8.10)

___________________________

Assisted Holiday Project Terms of Reference

Based on the Task Force recommendations, EAN undertook to pursue this area of work and in 2007 employed a worker to facilitate the assisted holiday project. The terms of reference for the project were as follows:

- Develop the assisted holiday programme as a pilot project resulting in the running of three to five programmes involving ten to twelve participants.

- Serve as a contact point between groups in Britain and groups in Ireland

- Assist groups in Ireland to coordinate activities of arriving group

- Produce a set of guidelines that will allow local groups to initiate assisted holiday programmes

- Assist organisations and community groups in fundraising for projects

- Undertake a public launch and publicity campaign to champion the project

The first assisted holiday took place in October 2007 to Clones, Co. Monaghan and was a partnership between Clones Community Forum and London Irish Centre, Camden. This holiday guided the production of this manual, as did participants’ feedback after the trip and direct observations by the EAN worker during the trip.

What is an assisted holiday?

About half a million Irish emigrants live  in Britain. Many of these are prospering, and there have been thousands of Irish emigrants who have returned home permanently in recent years.  Many others visit regularly, treasuring their time with family and friends as they reconnect with their birthplace.

For many, though, a trip home can seem an impossible dream.  Some people are facing their old age in poverty or isolated circumstances. Perhaps they do not have the money for a visit, or they may no longer have relations at home, or they may feel apprehensive about coming back if they have not been in Ireland for many years – or even decades. Some of them may have always held an image of Ireland as ‘home’ in their hearts, or even dreamed of returning to live. To lose the link with Ireland can be painful.

An assisted holiday brings Irish emigrants back home. It is an opportunity for an emigrant who would not otherwise be able to return to Ireland to do so, and for a local community in Ireland to participate in welcoming “home” a group of emigrants.

An assisted holiday is aimed at giving those Irish people abroad who would not return home on their own the opportunity to come home as part of a group trip, in a supportive environment, along with other Irish emigrants.

The recommended selection criteria for project participants reflects the requirement to benefit those older Irish people who are most in need of a return to Ireland.

In an Assisted Holiday the group is supported by staff and organisations in both countries. It is similar to a twinning programme in that the groups in two countries work together:

- a sending group in the UK organises the aspects of the trip that will allow the emigrants to return to Ireland

- a hosting group in Ireland welcomes the participants and arranges accommodation and activities for their stay.

Careful advance planning by both groups with clearly defined lines of responsibility is necessary to ensure the smooth and efficient running of the holiday.

This manual is intended as a set of guidelines to assist groups organise and facilitate assisted holiday projects.

Who can benefit?

The assisted holiday scheme is aimed at Irish emigrants of the 1930’s to the 1960’s who were either forced by economic necessity or chose to leave Ireland for other reasons during those times. The scheme is intended to benefit people aged 60+ and who may have some of the following characteristics:

  - People who live alone, are isolated and/or lonely

  - Those who have lost contact with family in Ireland

  - People who have not returned to Ireland in the previous three years (as a minimum requirement)

  - People who want to remain living in Britain, but wish to visit their home country

  - People who would like but are unable to return to Ireland to live

  - People on a low income and who have no other possibility of arranging or paying for a holiday

What can participants gain?

For many participants the holiday will be the first assisted group holiday in which they have participated. It is meant to be a highly enjoyable and memorable “trip of a lifetime”.

As most participants will not have been back for several years, the holiday will give participants an opportunity to re-connect with “home” in the following ways:

- It will offer the opportunity to

  - re-connect with family and friends,

  - renew and re-establish old friendships, and

  - restore connection with places, Irish culture and old memories.

- It is also a chance to make new friends and acquaintances.

- The holiday will also give participants an opportunity to consider if they would like to return to live in Ireland.

- For some, it may be a final but very significant trip home.

Why is there a need?

There is a proven need for assisted holidays for older emigrants. This is clearly documented in the Task Force Report as well as in feedback received from Irish organisations and individuals resident in the UK. There are significant numbers of older Irish emigrants living in exile who have lost contact with their homeland and who do not have sufficient resources to return home on holiday.

Many older people would love to have the opportunity to go to Ireland for a holiday but are unable to “do it alone”. Some of the reasons may include:

- They do not have the means to pay for such an experience

- They are unable to travel alone for reasons of frailty or other special needs

- They would find it too difficult, stressful or are nervous to go alone

- They have lost contact with relatives and have no place to stay

- Because of such a strong “sense of pride” they want to holiday independently of relatives

- They would like to have the emotional/practical support of an experienced worker

- They want to holiday in a group setting with like minded people  who share similar experiences of leaving Ireland (for example, losing contact with families)

- They do not have the resources to book a cost-efficient personal holiday to Ireland on the Internet

How can the holiday be funded?

It is imperative for the host and sending group to work together from an early stage to raise sufficient resources for an all-inclusive holiday. The cost of an assisted holiday includes the following as a minimum:

- flights

- insurance

- meals

- accommodation

- trips and outings

- supervision.

As an indication of the funding required, in 2008, the overall holiday cost worked out at approximately £500/€650 per person per week

How to divide costs?

Host Group Responsibilities

- Transport costs for the entire stay, including:

  - Collection and return to airport

  - Outings during the holiday

- Activities and outing costs which could include

  - venue admission fees

  - snacks

  - musicians

  - photographers

- Welcome meeting and farewell meeting,  including

  - refreshments

  - entertainment

  - room hire

- Staffing costs and volunteer expenses

Sending Group Responsibilities

- Transport costs to and from airport

- Helpers’ costs

- Costs of principal fundraising and supervision

- Staffing costs and volunteer expenses

- Miscellaneous other costs including, purchase of bags, clothes other items

Participants

- Those participants who have the resources should make some contribution towards the holiday.

- Some participants, however, may not be able to afford to contribute; they should not be excluded.

How to generate income?

- Seek sponsorship for various aspects of the holiday

  - Seek corporate and local business support

  - Write fundraising letters to local banks, newspapers and prominent individuals

- Organise funding events – a few suggestions:

  - Race night

  - Bingo

  - Dance

  - Afternoon tea

How to keep costs to a minimum

- Book the holiday as early as possible to get the best rates

- Travel and return mid-week

- Travel out of season

- Collect weekly contribution from participants well in advance

- Negotiate group deals from the accommodation centre

Where to stay?

It is the responsibility of the sending group to ensure that suitable accommodation is booked.  The Host Group may assist with local knowledge. If you need help identifying suitable venues, check with the Irish Tourist Board.

Here are some suggestions:

- Hotels are likely to be the best option. They often offer special deals in the off-season and you should try to negotiate a group rate.

- Bed and Breakfasts/Guesthouses – there are several excellent quality B&B’s and guesthouses who offer a homely environment at a very cost effective rate. Many will offer a home cooked meal in the evening and offer a personalised service to guests.

Importantly, if you use B&B’s you need to ensure there is a facility for participants to be able to return during the day. They may want refreshments, a rest, or to socialise with other participants. Some B&Bs do not want residents around during the day, so confirm that this is possible before you book.

- Holiday centres – there are some established holiday centres in Ireland and include centres operated by St. Vincent De Paul.  These centres offer an all inclusive package, which includes accommodation, meals, entertainment, trips, outings etc.. They will charge a weekly all-inclusive rate/individual. Most holiday centres are seasonal and therefore close during “out of season” times.

- Convents/Retreat Centres – There are some centres which can be hired out for the duration of the programme and may have special rates. Mount St. Anne’s Retreat Centre in Laois is one example.

- Youth hostels (An Óige) – Open to all age groups, youth hostels are often available in the off season for group bookings. For details contact: customerservices@anoige.ie

A town is a better choice of venue than a very rural location. Most participants will be accustomed to city life, and having all facilities and services at their doorstep. Some participants may prefer to go out before breakfast and get the morning paper or go to early morning mass.

How to travel?

In most cases, the group should travel by air, rather than coach and boat.

- Airfares are cheaper than ever

- Many older people are not able for the long trip by boat.

There may be some participants, however, who would prefer to travel by boat –

- Some people have a  fear of flying.

- The journey by boat may bring back old memories as most will have left Ireland as emigrants by boat.

Check out with participants their preferred mode of transport and book accordingly.

How long?

One week is the recommended length for a stay.

This gives people ample time to settle in and relax, while getting to know the area and enjoy the activities on offer.  The trip should be planned for mid-week (Wednesday to Wednesday, for example), as airfares and accommodation will usually be much cheaper.

How many participants?

Small groups work better. With a small group, members can get to know each other better and the group will bond together quickly. Members can also avail of closer support from helpers.

Have a maximum of 12 participants together with 2 helpers.

What kind of support for the trip?

Ideally, your helpers should have the following key attributes between them:

- A working knowledge of health and safety matters. (A nursing or caring background is most helpful.)

- Knowledge of the Host area and its services.

If any participant has a carer or partner who would like to come on the holiday, they should be encouraged to do so. However, they would have to cover the full cost of the holiday, unless they themselves are judged to qualify under the selection criteria.

Where?

It is ideal - but not essential - for participants to have originated from the area hosting the trip. There are several benefits for participants, including the following:

- They can easily visit or “track down” family or friends with whom they may have lost contact

- They can visit former places of interest and go down “memory lane”

- They can visit the graves of loved ones

- They can get a feel for the place and decide if they want to return to live there

- For those who do not want to stay with family/friends they can be independent and be in control

For some people, however, “leaving Ireland” is a sensitive subject so they may not want to go back to their county of birth. Some of these reasons could include the following:

- Returning to their birth-place might be too painful or sad if relatives have passed away

- Some emigrants may feel excluded from their family in Ireland and find it hard to go back as there might be unresolved issues too difficult to surmount

- They may have entirely lost any home county connections

Ultimately, the Host area selection may be determined by the availability of a Host group willing to host.

It is worth discussing all of the above factors beforehand with participants, before they make a final decision to be included or not on the holiday.

What will participants do?

It is important to have a well planned programme for the entire stay, which should feature both daily and weekly plans. This helps the group have a focus each day and ensures that participants do not lose interest or get bored.

- Build in ample free time.

- Don’t have activities going on too late in the evening or too early in the morning.

- Gather information from participants in advance about their interests and use this to help structure the timetable.

- Cater for different activity levels: Some will want to be very busy. Others will appreciate more time to relax.

Cultural and historical trips and outings are of particular interest. Consider trips to museums, local exhibitions, castles, parks, historical monuments and tourist trails.

Social meetings

- A pre-departure social evening will help people get acquainted and help them look forward to the trip. It can also be an opportunity to pre-plan activities and trips for the week.

- A welcome meeting by the host group is a good way to start off the week. This is an opportunity to meet and get to know members of the host group as well as discuss the programme of events and answer any questions that may arise.

- A farewell event will brings closure to the week and gives the participants and the host group an opportunity to say “thank-you” and “goodbye”.

The welcome and farewell event could include a buffet, Irish music and dancing.

What information to collect?

It is important to have detailed information on each participant while respecting and protecting the privacy of each individual. At the end of this set of guidelines is a Basic Information Form, which should be completed for each individual participant. This includes essential personal information as well as information on expectations from the trip and participant’s individual interests.

Complete the Basic Information form well in advance – use it to assist the planning of activities and events.

Confidentiality of information is paramount.

Do not disclose personal information to any person or organisation unless it is:

- absolutely necessary

- agreed by the participant and

- in full accordance with data protection legislation in both countries.

Each participant should complete a consent form which gives permission to share relevant information (see form at end of section)

It will be important to pass on information on specific medical, dietary or other needs for participant health, catering and accommodation purposes.

Take the first steps.

See Critical Path Analysis on page 23.

- If your organisation is interested in setting up an assisted holiday scheme either as Source (UK) or Host (Ireland), agree a named person to be the holiday co-ordinator.

- Identify and agree a partner organisation – you may already have established links with certain groups or you could contact umbrella groups in Britain (Federation of Irish Societies) or Ireland (EAN) for assistance (see useful address section).  You may find a suitable partner in the relevant section of this website.

- Both groups should meet to discuss partnership arrangements and responsibilities and plan the holiday at least 6 months in advance.

- The sending and host groups should compile a budget detailing the various costs of the trip for both groups.

- Both groups should actively fundraise to cover the costs.

- This budget should include how much participants are expected to contribute as well as criteria for free places (if any).

- A provisional date should be set and accommodation, activities etc should be provisionally booked.

- The final date should be agreed once funding has been confirmed.

- Confirm accommodation and book flights.

- Plan a programme of activities, events, outings and produce a timetable which will be given to each participant.

- Collate a participant information pack which will include–

- what to see and do in the area

- telephone numbers of local doctors, hospitals, hairdressers and other services

- church location and times

- shops

- a map

What are the duties of the sending group?

The sending group will need to have the capacity to facilitate and organise the assisted holiday. There is much work involved: the group should have a committee in place with at least one staff member or volunteer who can devote considerable time to the project.

Advance planning:

- Nominate a named link person in the source area to facilitate the trip.

- Agree on holiday participant criteria with host group, for example:

  - when last in Ireland

  - carers or partners allowed

  - free or minimal cost places

- Advertise locally in parish newsletters, papers, elders services etc.

- Funding – how will the trip be paid for? who will fundraise?

- How much will participants contribute?

- Who will be going on the Holiday (Leader and helper)?

- How do you select participants, especially if over-subscribed?

- Organise transport to and from airport.

When the participants are chosen:

- Ensure all participants have suitable ID i.e. passports. Take a copy for future use.

- Ensure all participants have a European Health Insurance Card (EHIC). This can be obtained by application online at http://www.ehic.org.uk or at the local post office, usually taking approx 1 month to acquire from date of application.

- Ensure Information Sheets are thoroughly completed and non-confidential information shared with host group.

- Complete consent forms for all participants.

- Carry out a written risk assessment of the trip and plan to mitigate any associated risks. See suggested form on this website.

- Pack a first aid box for minor health emergencies

- Do participants need help with shopping/packing for trip?

- Shared rooms – agree who will share in advance. Also check if participants need to have a shower instead of a bath.

Just before and during the holiday:

- Get a printout of participants’ medication regimes and information on any health conditions. Ensure participants have ample medication supplies for the holiday.

- Agree a meeting point on the day and drop off point on return. Consider having a welcome back “tea/meal” and driving individuals  directly to their home afterwards.

After the holiday:

- Organise a participant review meeting and discussion within a month after the holiday takes place.

- Do the group wish to continue to meet after the holiday?

What will the host group do?

It is necessary for the Host group to have the capacity to facilitate and organise an assisted holiday. The group should have a committee in place with at lease one staff member or volunteer who can devote time to the this project.

- Book accommodation in consultation with sending group

- Arrange transport for entire stay – collection and drop-off to airport, activities

- Compile a Programme of Activities based on information received from Sending Group

- Enlist volunteers for the daily/evening activities

- Enlist the assistance of local community activists for the holiday, this can include musicians, singers, local businesses, press

- Compile an Information Pack on the local area to include Emergency Services, GP’s, Church times, history of local area, places to see

- Arrange a Welcome meeting and a Farewell meeting. Involve musicians and local groups if possible.

- Funding – Approach local St. Vincent De Paul, Lions Clubs, Chamber of Commerce, Church

Consider these activities

- Local places of interest to include museums and theatres

- Scenic drive in the countryside (not on motorways)

- Trip to local shopping centre

- Afternoon tea in hotel

- Visit to local day centre, sheltered housing

- Historical walk of village/town

- Trip to beach (if nearby)

- Irish music session or concert

- Bingo

- Religious or other local festivals

Ensure health and safety

The sending group and holiday leader are responsible for the health, safety and welfare of participants throughout the holiday.

Carry out an advance risk assessment of the holiday.

Conduct regular head counts of participants at key points, especially

  - before and immediately after travel, events and activities,

  - at mealtimes and

  - before retiring each evening.

Holiday leader duties

The holiday leader should at all times:

- Carry a list of participant details

- Carry local emergency and other health telephone numbers

- Carry a mobile phone and

- Ensure every day that all participants have the mobile phone number and any other contact details.

- Carry the first aid kit.

S/he should ensure the following:

- there are adequate protections for night-time safety and security of participants at the selected accommodation.

- that any alcohol and tobacco policy agreed by the group or related to a hosting facility is complied with.

- that s/he is familiar with and takes action to mitigate additional risks attached to such factors as

  - to poor weather

  - seaside/ hillside/ farm visits

  - transport use.

Involve the participants

User involvement is an essential component of a successful assisted holiday. Older people are often excluded and are viewed as passive recipients of services. The holiday project is a partnership of all concerned according to their varying needs, skills and experiences.

The Assisted Holidays guests should be involved in all stages of planning and delivery of the holiday including the timetable, risk assessment, formulating a code of behaviour.

Personal Information Sheet

| Name |  |
| --- | --- |
| Address |  |
| Telephone number |  |
| Age and Date of Birth |  |
| Place of Birth |  |
| Date left Ireland and date you last visited |  |
| Do you still have family/friends living in Ireland? |  |
| Interests (eg music, bingo, reading, walking, shopping) |  |
| Reasons why you would like to go on this assisted holiday (eg. Visit family, friends, go to see graves. Visit former places of interest) |  |
| Next of Kin details (name, telephone number, address) |  |
| GP details (name, telephone number, address) |  |
| Health details, including any diagnosis |  |
| Medication details (Name, frequency, amount etc) |  |
| Do you have a carer or partner that you would like to take with you? |  |
| Are you able to pay or contribute towards the cost of the holiday? |  |
| Any Other Information you might like to add (eg. special diet) |  |

Signed  	________________________________________

Signed 	________________________________________

Date 		________________________________________

| Office Use |  |
| --- | --- |
| Valid Identity for travel – e.g. passport, Keep a copy on file European Health Insurance Card (EHIC) - for NHS Treatment. Keep a copy on file. Health and medication details received Insurance booked and details confirmed Any additional personal requirements |  |

Assisted Holiday Consent Form

I ___________________ duly authorise _________________ to share the following information about me if required to do so at any stage of the holiday to/ from Ireland on _____________ of which I am a participant.

Medical and health details

Details of medication

Next of kin details

I also consent to _________________  contacting the following on my behalf

Doctor

Hospital

Next of Kin

Signed        ______________________________

Date 		______________________________

Risk Assessment Form

Critical Path Analysis

As outlined earlier in this manual we recommend a minimum of a six month lead-up to the actual date of the assisted holiday.

| Month | Action |
| --- | --- |
| Preparation Month 1 | - Confirm and agree partner group in writing - Agree tasks (see page x for guidelines) - Confirm funding arrangements and agree who applies and to whom, for any shortfall (see page x for guidelines) - Agree criteria for selection of participants |
| Month 2 | - Advertise holiday in local papers, church, Irish centres, social clubs - Make provisional booking for accommodation |
| Month 3 | - Commence interview/selection process - Continue fundraising efforts |
| Month 4 | - Confirm participants and check each participant has relevant Identity - Apply for passports or national Identity card if necessary - Apply for European Health Insurance Card (EHIC), if required - Book flights - Confirm accommodation |
| Month 5 | - Carry out a risk assessment of the trip and plan to mitigate risks - Compile programme of activities and useful information sheet - Complete Basic Information Sheet for each participant |
| Month 6 (Departure) | - Hold a pre-departure social evening - Confirm transport arrangements to/from airport each side - Ensure First Aid box and participant personal data sheets with travel are completed - Confirm possession of all other required holiday information with travel - Check with participants they have ample medication supplies, where applicable - Agree meeting point, code of behaviour etc.. (see checklist page x) - Hold a return home event (a few weeks after the holiday) |

Checklist on Departure Day

(more to be added after Clare holiday)

| Action | Completed |
| --- | --- |
| Check each participant has relevant ID (Passport/Drivers Licence) |  |
| Check each participant has their medication with them |  |
| Check each participant has EHIC card |  |
| Distribute Timetable to each participant |  |
| Give each participant Holiday Leader contact details |  |
| Check each participant has handbag/hand luggage |  |
| Agree code of behaviour/ground rules e.g. punctuality for t trips, rules regarding smoking |  |
| Agree meeting point in the event of participants getting lost |  |

The Monaghan Experience 
Clones 10th to 17th October 2007

(Picture)

The first assisted holiday Pilot Project took place in October 2007. It was hosted by Clones Community Forum and partnered with The London Irish Centre in Camden. The holiday group comprised of eight older people and two helpers, one of whom was a registered nurse. Most participants had not been back for at least 5 years and all came from County Monaghan and surrounding Counties.

Clones Community Forum was founded in 1988 as a result of a Social Needs Analysis of Clones which was commissioned by the Programme for Peace and Reconciliation. Its objective was to identify social needs and support social infrastructure in Clones and its surrounding hinterland. The Forum was formed to address the social need and use a community development approach to rebuild fractured community relations.

Camden Irish Centre was established in 1957 and aims to respond to the unmet needs among Irish people in London. The Centre provides a range of culturally sensitive and supportive welfare advice/advocacy and training service which celebrates and promotes Irish culture.

The holiday was a “trip of a lifetime” for all participants and there was an unanimous consensus that it was “their best holiday ever”. Clones Community Forum is a model of good practice and is commended on facilitating such a successful and enjoyable trip. The hospitality, friendliness, community spirit, fun, professionalism was noted by all participants and they ensured participants returned to London with positive memories of Ireland.

The overall experience of the Holiday was positive and as it was a Pilot Project, it afforded Ean the opportunity to learn from mistakes and make the next trips “even better”.

OUTCOMES

- One member had not been home for 25 years since the death of his wife and lost all contact with his family (Enniskillen). We re-united him with his brother and extended family.

- One member had not been back to his home village for 48 years (near Carrickmacross). We took him to his village, took photos and he met a distant relative. He is now planning a trip “home” in March 2008.

- One member had not been back for 15 years and did not know if her sister was still alive (Clones). We re-united her with all her family and she met her sister who now lives in a Nursing Home and is aged 90.

- We arranged a surprise and tearful re-union for one member with her sister and a surprise visit to our Farewell party by three further sisters (Donegal)

- We arranged a surprise re-union for another two members (brothers) with their sister who travelled all the way form Sligo to see them.

- Another member visited her family for the day (near Clones). She had previously returned to live in Ireland but she could not settle and returned to London.

Pictures 3 and 4

What Worked Well

- Excellent planning by host group (Clones Community Forum)

- Structured timetable for the week to suit all needs/preferences

- Lovely accommodation and excellent food

- Most participants were from Monaghan and surrounding counties

- The group gelled very well and the small group worked well

- The holiday was fully funded through a grant from the Department of Social and Family Affairs

Areas for Improvement

- Longer period of time required for planning trip

- Better communication between the two groups prior to the trip

- Flexibility of criteria for holiday

- Participants to contribute towards the cost of the trip and activities

- Members to pay a small holiday deposit in advance

- Have one or two drop-off and collection points

- Have earlier flight times back to UK

- Group in the UK to meet a few times before holiday

Useful Web Addresses

Department of Social and Foreign Affairs

http://www.welfare.ie

Díon Committee -

Federation of Irish Societies

http://www.irishsocieties.org

Irish Tourist Board

www.discoverireland.ie

Chamber of Commerce of Ireland (sources of funding)- http://www.chambers.ie

Lions Club (as above)

http://www.lionsclub.org

St Vincent De Paul (as above)

http://www.svp.ie

The Irish Embassy (London)

http://www.embassyofireland.co.uk

The Irish Embassy Passport Office

http://www.embassyofireland.co.uk/home/index.aspx?id=33715

Tel:020 – 7225 7700

Department of Health

http://www.dohc.ie

National Health Service

http://www.nhs.uk

RyanAir

www.ryanair.com

Aer Lingus

www.aerlingus.com

Stena Line

http://www.stenaline.co.uk

Irish Ferries

http://www.irishferries.co.uk

Irish Airports

Dublin – http://www.dublinairport.com

Shannon – http://www.shannonairport.com

Cork – http://www.corkairport.com

Knock – http://www.knockairport.com

Belfast – http://www.belfastairport.com